## Лист1
Project | ID | Create Date | Summary | Status | Priority | Severity | Description | Environment | Affects Version | Reporter
Payment | 0.01 | 2019-01-24 | [UI] Syntax error | new | Medium | Minor | In upper right corner of bloc "Silver" present syntax error in word "Popular" ER: Most Popular AR: Most Populr | Chrome 70.0.3538.102
Payment | 0.02 | 2019-01-24 | [Functional] Button Subscribe in bloc "Platinum" is not work | new | Higt | Critical | Button Subscribe in bloc "Platinum" does not call required function ER: Opened window "Payment Details" AR: Window "Payment Details" is not open | Chrome 70.0.3538.102
Payment | 0.03 | 2019-01-24 | [UI] Symbol mapping error | new | Medium | Minor | 1. Push button Subscribe in bloc Bronze 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" valid value. 6. Push button Pay ER: Stripe user detected! AR: Stripe user detected! 😱 | Chrome 70.0.3538.102
Payment | 0.04 | 2019-01-24 | [Functional] Button Remember does not remember Peyment details in all subscription plans | new | Major | Medium | 1. Push button Subscribe in any bloc of subscription plan 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" valid value. 6. Tick the checkbox Remember. 7. Push button Pay. 8. Push button Esc. 9. Push button Subscribe in any bloc of subscription plan ER: Payment details is already written. AR: Payment datails is empty.
Payment | 0.05 | 2019-01-24 | [Functional] There is an extra text box "Billing Address" | new | Higt | Major | 1. Push button Subscribe in any bloc of subscription plan. ER: There are Text boxes: "Your name", "Card Number", "Expiry Date", "Code CV". AR: There are Text boxes: "Your name", "Bulling Address", "Card Number", "Expiry Date", "Code CV".
Payment | 0.06 | 2019-01-24 | [Functional] The text box "Your Name" contains not enough symbols | new | Higt | Medium | 1. Push button Subscribe in any bloc of subscription plan. 2. Enter in field "Your Name" max number of characters. ER: max numbers of characters within 25-35 symbols AR: max numbers of characters within 17 symbols (this is not enough)
Payment | 0.07 | 2019-01-24 | [Functional] Subscription plan "Bronze" accepts cards with invalid "Code CV" | new | Higt | Critical | 1. Push button Subscribe in bloc Bronze 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" invalid value. 6. Push button Pay ER: Error massage: Charge is declined with an incorrect CV code. AR: Stripe user detected! 😱
Payment | 0.08 | 2019-01-24 | [Functional] Subscription plan "Bronze" accepts cards with invalid "Expiry Date" | new | Higt | Critical | 1. Push button Subscribe in bloc Bronze 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" invalid value. 5. Enter in field "Code CV" valid value. 6. Push button Pay ER: Error massage: Charge is declined with an expired card code. AR: Stripe user detected! 😱
Payment | 0.09 | 2019-01-24 | [Functional] Subscription plan "Silver" does not accepts cards with valid "CV Code" | new | Higt | Critical | 1. Push button Subscribe in bloc Silver 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" valid value. 6. Push button Pay ER: Stripe user detected! AR: Charge is declined with a card_declined code.
Payment | 0.10 | 2019-01-24 | [Functional] Subscription plan "Silver" does not accepts cards with valid values | new | Higt | Critical | 1. Push button Subscribe in bloc Silver 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" valid value. 6. Push button Pay ER: Stripe user detected! AR:Error massage: Charge is declined with a card_declined code. OR Charge is declined with a processing_error code. OR Charge succeeds and domestic pricing is used (other test cards use international pricing). This card is only significant in countries with split pricing.
Payment | 0.11 | 2019-01-24 | [Functional] Subscription plan "Gold" does not accepts cards with valid values | new | Higt | Critical | 1. Push button Subscribe in bloc Silver 2. Enter in field "Your name" valid value. 3. Enter in field "Card Number" valid value. 4. Enter in field "Expiry Date" valid value. 5. Enter in field "Code CV" valid value. 6. Push button Pay ER: Stripe user detected! AR:Error massage: Charge is declined with an incorrect_cvc code. OR Charge is declined with a processing_error code. OR Charge succeeds and funds will be added directly to your available balance (bypassing your pending balance). OR Charge is declined with a card_declined code.